## time_phased_budget
Date | Week | Day | Backend Developer | Branch Manager | Business Analyst | Database Administrator | Delivery Operations Manager | External Auditor | Frontend Developer | Legal Consultant | Marketing Manager | Project Manager | QA Tester | Rider Coordinator | Technical Lead | UI/UX Designer | Fixed Costs | Daily Total (PKR) | Cumulative Total (PKR)
2025-12-01 | 1 | Monday | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 3600 | 0 | 5961.54 | 75761.54 | 75761.54
2025-12-02 | 1 | Tuesday | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 3600 | 0 | 5961.54 | 75761.54 | 151523.08
2025-12-03 | 1 | Wednesday | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 3600 | 0 | 5961.54 | 75761.54 | 227284.62
2025-12-04 | 1 | Thursday | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 3600 | 0 | 5961.54 | 75761.54 | 303046.15
2025-12-05 | 1 | Friday | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 3600 | 0 | 5961.54 | 75761.54 | 378807.69
2025-12-08 | 2 | Monday | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 37800 | 0 | 5961.54 | 66961.54 | 445769.23
2025-12-09 | 2 | Tuesday | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 37800 | 0 | 5961.54 | 66961.54 | 512730.77
2025-12-10 | 2 | Wednesday | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 37800 | 0 | 5961.54 | 66961.54 | 579692.31
2025-12-11 | 2 | Thursday | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 37800 | 0 | 5961.54 | 66961.54 | 646653.85
2025-12-12 | 2 | Friday | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 37800 | 0 | 5961.54 | 66961.54 | 713615.38
2025-12-15 | 3 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 5961.54 | 24961.54 | 738576.92
2025-12-16 | 3 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 5961.54 | 24961.54 | 763538.46
2025-12-17 | 3 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 5961.54 | 24961.54 | 788500
2025-12-18 | 3 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 5961.54 | 24961.54 | 813461.54
2025-12-19 | 3 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 5961.54 | 24961.54 | 838423.08
2025-12-22 | 4 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5961.54 | 25961.54 | 864384.62
2025-12-23 | 4 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5961.54 | 25961.54 | 890346.15
2025-12-24 | 4 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5961.54 | 25961.54 | 916307.69
2025-12-25 | 4 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5961.54 | 25961.54 | 942269.23
2025-12-26 | 4 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 5961.54 | 25961.54 | 968230.77
2025-12-29 | 5 | Monday | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 5961.54 | 56961.54 | 1025192.31
2025-12-30 | 5 | Tuesday | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 5961.54 | 56961.54 | 1082153.85
2025-12-31 | 5 | Wednesday | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 5961.54 | 56961.54 | 1139115.38
2026-01-01 | 5 | Thursday | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 5961.54 | 56961.54 | 1196076.92
2026-01-02 | 5 | Friday | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 5961.54 | 56961.54 | 1253038.46
2026-01-05 | 6 | Monday | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 5961.54 | 68761.54 | 1321800
2026-01-06 | 6 | Tuesday | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 5961.54 | 68761.54 | 1390561.54
2026-01-07 | 6 | Wednesday | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 5961.54 | 68761.54 | 1459323.08
2026-01-08 | 6 | Thursday | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 5961.54 | 68761.54 | 1528084.62
2026-01-09 | 6 | Friday | 0 | 0 | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 5961.54 | 68761.54 | 1596846.15
2026-01-12 | 7 | Monday | 15600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 27161.54 | 1624007.69
2026-01-13 | 7 | Tuesday | 15600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 27161.54 | 1651169.23
2026-01-14 | 7 | Wednesday | 15600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 27161.54 | 1678330.77
2026-01-15 | 7 | Thursday | 15600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 27161.54 | 1705492.31
2026-01-16 | 7 | Friday | 15600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 27161.54 | 1732653.85
2026-01-19 | 8 | Monday | 38400 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 48561.54 | 1781215.38
2026-01-20 | 8 | Tuesday | 38400 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 48561.54 | 1829776.92
2026-01-21 | 8 | Wednesday | 38400 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 48561.54 | 1878338.46
2026-01-22 | 8 | Thursday | 38400 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 48561.54 | 1926900
2026-01-23 | 8 | Friday | 38400 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 48561.54 | 1975461.54
2026-01-26 | 9 | Monday | 22800 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 46761.54 | 2022223.08
2026-01-27 | 9 | Tuesday | 22800 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 46761.54 | 2068984.62
2026-01-28 | 9 | Wednesday | 22800 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 46761.54 | 2115746.15
2026-01-29 | 9 | Thursday | 22800 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 46761.54 | 2162507.69
2026-01-30 | 9 | Friday | 22800 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 46761.54 | 2209269.23
2026-02-02 | 10 | Monday | 31200 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 58761.54 | 2268030.77
2026-02-03 | 10 | Tuesday | 31200 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 58761.54 | 2326792.31
2026-02-04 | 10 | Wednesday | 31200 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 58761.54 | 2385553.85
2026-02-05 | 10 | Thursday | 31200 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 58761.54 | 2444315.38
2026-02-06 | 10 | Friday | 31200 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 58761.54 | 2503076.92
2026-02-09 | 11 | Monday | 32400 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 61161.54 | 2564238.46
2026-02-10 | 11 | Tuesday | 32400 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 61161.54 | 2625400
2026-02-11 | 11 | Wednesday | 32400 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 61161.54 | 2686561.54
2026-02-12 | 11 | Thursday | 32400 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 61161.54 | 2747723.08
2026-02-13 | 11 | Friday | 32400 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 61161.54 | 2808884.62
2026-02-16 | 12 | Monday | 8400 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 39561.54 | 2848446.15
2026-02-17 | 12 | Tuesday | 8400 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 39561.54 | 2888007.69
2026-02-18 | 12 | Wednesday | 8400 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 39561.54 | 2927569.23
2026-02-19 | 12 | Thursday | 8400 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 39561.54 | 2967130.77
2026-02-20 | 12 | Friday | 8400 | 0 | 0 | 0 | 0 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 39561.54 | 3006692.31
2026-02-23 | 13 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3039053.85
2026-02-24 | 13 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3071415.38
2026-02-25 | 13 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3103776.92
2026-02-26 | 13 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3136138.46
2026-02-27 | 13 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3168500
2026-03-02 | 14 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 35961.54 | 3204461.54
2026-03-03 | 14 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 35961.54 | 3240423.08
2026-03-04 | 14 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 35961.54 | 3276384.62
2026-03-05 | 14 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 35961.54 | 3312346.15
2026-03-06 | 14 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 35961.54 | 3348307.69
2026-03-09 | 15 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 34761.54 | 3383069.23
2026-03-10 | 15 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 34761.54 | 3417830.77
2026-03-11 | 15 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 34761.54 | 3452592.31
2026-03-12 | 15 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 34761.54 | 3487353.85
2026-03-13 | 15 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 34761.54 | 3522115.38
2026-03-16 | 16 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3554476.92
2026-03-17 | 16 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3586838.46
2026-03-18 | 16 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3619200
2026-03-19 | 16 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3651561.54
2026-03-20 | 16 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 32361.54 | 3683923.08
2026-03-23 | 17 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 5961.54 | 22961.54 | 3706884.62
2026-03-24 | 17 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 5961.54 | 22961.54 | 3729846.15
2026-03-25 | 17 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 5961.54 | 22961.54 | 3752807.69
2026-03-26 | 17 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 5961.54 | 22961.54 | 3775769.23
2026-03-27 | 17 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 5961.54 | 22961.54 | 3798730.77
2026-03-30 | 18 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 5961.54 | 31961.54 | 3830692.31
2026-03-31 | 18 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 5961.54 | 31961.54 | 3862653.85
2026-04-01 | 18 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 5961.54 | 31961.54 | 3894615.38
2026-04-02 | 18 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 5961.54 | 31961.54 | 3926576.92
2026-04-03 | 18 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0 | 0 | 0 | 5961.54 | 31961.54 | 3958538.46
2026-04-06 | 19 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 5961.54 | 33961.54 | 3992500
2026-04-07 | 19 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 5961.54 | 33961.54 | 4026461.54
2026-04-08 | 19 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 5961.54 | 33961.54 | 4060423.08
2026-04-09 | 19 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 5961.54 | 33961.54 | 4094384.62
2026-04-10 | 19 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 5961.54 | 33961.54 | 4128346.15
2026-04-13 | 20 | Monday | 9600 | 0 | 8400 | 8400 | 0 | 32000 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 0 | 5961.54 | 82361.54 | 4210707.69
2026-04-14 | 20 | Tuesday | 9600 | 0 | 8400 | 8400 | 0 | 32000 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 0 | 5961.54 | 82361.54 | 4293069.23
2026-04-15 | 20 | Wednesday | 9600 | 0 | 8400 | 8400 | 0 | 32000 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 0 | 5961.54 | 82361.54 | 4375430.77
2026-04-16 | 20 | Thursday | 9600 | 0 | 8400 | 8400 | 0 | 32000 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 0 | 5961.54 | 82361.54 | 4457792.31
2026-04-17 | 20 | Friday | 9600 | 0 | 8400 | 8400 | 0 | 32000 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 0 | 5961.54 | 82361.54 | 4540153.85
2026-04-20 | 21 | Monday | 18000 | 0 | 19600 | 12600 | 4800 | 0 | 0 | 0 | 16800 | 0 | 0 | 26000 | 7200 | 0 | 5961.54 | 110961.54 | 4651115.38
2026-04-21 | 21 | Tuesday | 18000 | 0 | 19600 | 12600 | 4800 | 0 | 0 | 0 | 16800 | 0 | 0 | 26000 | 7200 | 0 | 5961.54 | 110961.54 | 4762076.92
2026-04-22 | 21 | Wednesday | 18000 | 0 | 19600 | 12600 | 4800 | 0 | 0 | 0 | 16800 | 0 | 0 | 26000 | 7200 | 0 | 5961.54 | 110961.54 | 4873038.46
2026-04-23 | 21 | Thursday | 18000 | 0 | 19600 | 12600 | 4800 | 0 | 0 | 0 | 16800 | 0 | 0 | 26000 | 7200 | 0 | 5961.54 | 110961.54 | 4984000
2026-04-24 | 21 | Friday | 18000 | 0 | 19600 | 12600 | 4800 | 0 | 0 | 0 | 16800 | 0 | 0 | 26000 | 7200 | 0 | 5961.54 | 110961.54 | 5094961.54
2026-04-27 | 22 | Monday | 7200 | 0 | 15400 | 0 | 19200 | 0 | 15600 | 0 | 3600 | 4000 | 4000 | 12000 | 0 | 5000 | 5961.54 | 91961.54 | 5186923.08
2026-04-28 | 22 | Tuesday | 7200 | 0 | 15400 | 0 | 19200 | 0 | 15600 | 0 | 3600 | 4000 | 4000 | 12000 | 0 | 5000 | 5961.54 | 91961.54 | 5278884.62
2026-04-29 | 22 | Wednesday | 7200 | 0 | 15400 | 0 | 19200 | 0 | 15600 | 0 | 3600 | 4000 | 4000 | 12000 | 0 | 5000 | 5961.54 | 91961.54 | 5370846.15
2026-04-30 | 22 | Thursday | 7200 | 0 | 15400 | 0 | 19200 | 0 | 15600 | 0 | 3600 | 4000 | 4000 | 12000 | 0 | 5000 | 5961.54 | 91961.54 | 5462807.69
2026-05-01 | 22 | Friday | 7200 | 0 | 15400 | 0 | 19200 | 0 | 15600 | 0 | 3600 | 4000 | 4000 | 12000 | 0 | 5000 | 5961.54 | 91961.54 | 5554769.23
2026-05-04 | 23 | Monday | 0 | 0 | 14000 | 0 | 9600 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 36000 | 0 | 5961.54 | 73561.54 | 5628330.77
2026-05-05 | 23 | Tuesday | 0 | 0 | 14000 | 0 | 9600 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 36000 | 0 | 5961.54 | 73561.54 | 5701892.31
2026-05-06 | 23 | Wednesday | 0 | 0 | 14000 | 0 | 9600 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 36000 | 0 | 5961.54 | 73561.54 | 5775453.85
2026-05-07 | 23 | Thursday | 0 | 0 | 14000 | 0 | 9600 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 36000 | 0 | 5961.54 | 73561.54 | 5849015.38
2026-05-08 | 23 | Friday | 0 | 0 | 14000 | 0 | 9600 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 36000 | 0 | 5961.54 | 73561.54 | 5922576.92
2026-05-11 | 24 | Monday | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 20361.54 | 5942938.46
2026-05-12 | 24 | Tuesday | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 20361.54 | 5963300
2026-05-13 | 24 | Wednesday | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 20361.54 | 5983661.54
2026-05-14 | 24 | Thursday | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 20361.54 | 6004023.08
2026-05-15 | 24 | Friday | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 5961.54 | 20361.54 | 6024384.62
2026-05-18 | 25 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 5961.54 | 25961.54 | 6050346.15
2026-05-19 | 25 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 5961.54 | 25961.54 | 6076307.69
2026-05-20 | 25 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 5961.54 | 25961.54 | 6102269.23
2026-05-21 | 25 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 5961.54 | 25961.54 | 6128230.77
2026-05-22 | 25 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 8000 | 0 | 0 | 5961.54 | 25961.54 | 6154192.31
2026-05-25 | 26 | Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 5961.54 | 39961.54 | 6194153.85
2026-05-26 | 26 | Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 5961.54 | 39961.54 | 6234115.38
2026-05-27 | 26 | Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 5961.54 | 39961.54 | 6274076.92
2026-05-28 | 26 | Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 5961.54 | 39961.54 | 6314038.46
2026-05-29 | 26 | Friday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 5961.54 | 39961.54 | 6354000

## project_summary
Column1 | Column2 | Column3 | Column4
FOODHUB PROJECT - BUDGET SUMMARY
Project Information
Project Name | FoodHub - Online Food Ordering & Delivery Management System
Start Date | 2025-12-01
End Date | 2026-05-31
Duration | 26 weeks (6 months)
Total Activities | 186
Cost Breakdown by Resource Type
Resource | Total Hours | Hourly Rate (PKR) | Total Cost (PKR)
Backend Developer | 318.0 | 3000 | 954000.00
Branch Manager | 0.0 | 3500 | 0.00
Business Analyst | 148.0 | 3500 | 518000.00
Database Administrator | 108.0 | 3500 | 378000.00
Delivery Operations Manager | 68.0 | 3000 | 204000.00
External Auditor | 20.0 | 8000 | 160000.00
Frontend Developer | 358.0 | 3000 | 1074000.00
Legal Consultant | 0.0 | 5000 | 0.00
Marketing Manager | 46.0 | 3000 | 138000.00
Project Manager | 98.0 | 5000 | 490000.00
QA Tester | 178.0 | 2500 | 445000.00
Rider Coordinator | 92.0 | 2500 | 230000.00
Technical Lead | 94.0 | 4500 | 423000.00
UI/UX Designer | 226.0 | 2500 | 565000.00
Total Labor Costs |  |  | 5579000.00
Fixed Costs Summary
Category | Amount (PKR)
Background Checks (20 riders) | 20000
Cloud Setup Fees | 30000
Delivery Bags (30 units) | 150000
Development Licenses | 50000
Google Maps API Credits | 25000
Job Advertisement Postings | 10000
Legal Consultation | 50000
Marketing Materials Printing | 50000
Professional Photography | 30000
Rider Uniforms (20 sets) | 60000
SMS Gateway Credits | 15000
SSL Certificates | 15000
Security Audit | 100000
Smartphone Accessories | 50000
Vehicle Branding | 40000
Video Production | 80000
Total Fixed Costs | 775000
PROJECT TOTALS
Total Labor Costs | 5579000.00
Total Fixed Costs | 775000
Contingency (15%) | 953100.00
GRAND TOTAL | 7307100.00
Cost by Phase
Phase | Weeks | Total Cost (PKR)
1.0 Initiation & Planning | 1-2 | 713615.38
2.0 Design | 3-6 | 883230.77
3.0 Development | 7-16 | 2087076.92
4.0 Testing & QA | 17-20 | 856230.77
5.0 Deployment | 21-22 | 1014615.38
6.0 Operational Setup | 21-22 | 1014615.38
7.0 Launch & Stabilization | 23-26 | 799230.77

## activity_cost_sheet
WBS Code | Activity Name | Resource | Hours | Hourly Rate (PKR) | Total Cost (PKR) | Week
2001-01-01 | Conduct project kickoff meeting with stakeholders | Project Manager | 4 | 5000 | 20000 | 1
2002-01-01 | Define and approve project charter | Project Manager | 8 | 5000 | 40000 | 1
2003-01-01 | Establish project governance and communication structure | Project Manager | 6 | 5000 | 30000 | 1
2004-01-01 | Conduct stakeholder identification and create register | Business Analyst | 6 | 3500 | 21000 | 1
2005-01-01 | Schedule expert consultant sessions | Project Manager | 2 | 5000 | 10000 | 1
2006-01-01 | Set up project repository and documentation tools | Technical Lead | 4 | 4500 | 18000 | 1
2001-01-02 | Conduct customer needs analysis workshop | Business Analyst | 8 | 3500 | 28000 | 1
2002-01-02 | Interview restaurant staff for operational requirements | Business Analyst | 6 | 3500 | 21000 | 1
2003-01-02 | Gather delivery rider requirements | Business Analyst | 4 | 3500 | 14000 | 1
2004-01-02 | Document functional requirements for all systems | Business Analyst | 16 | 3500 | 56000 | 1
2005-01-02 | Create use case diagrams for all user types | Business Analyst | 12 | 3500 | 42000 | 1
2006-01-02 | Validate requirements with stakeholders | Business Analyst | 6 | 3500 | 21000 | 1
2007-01-02 | Finalize requirements document with expert approval | Business Analyst | 8 | 3500 | 28000 | 1
2001-01-03 | Evaluate and select technology stack | Technical Lead | 8 | 4500 | 36000 | 2
2002-01-03 | Design high-level system architecture | Technical Lead | 12 | 4500 | 54000 | 2
2003-01-03 | Select cloud hosting provider and services | Technical Lead | 6 | 4500 | 27000 | 2
2004-01-03 | Select payment and SMS gateway providers | Technical Lead | 8 | 4500 | 36000 | 2
2005-01-03 | Set up development environments | Technical Lead | 8 | 4500 | 36000 | 2
2006-01-03 | Establish version control and CI/CD pipeline | Backend Developer | 12 | 3000 | 36000 | 2
2007-01-03 | Finalize project plan with WBS and timeline | Project Manager | 16 | 5000 | 80000 | 2
2001-02-01 | Conduct user research and create personas | UI/UX Designer | 12 | 2500 | 30000 | 3
2002-02-01 | Create user journey maps and information architecture | UI/UX Designer | 10 | 2500 | 25000 | 3
2003-02-01 | Design wireframes for all customer app screens | UI/UX Designer | 16 | 2500 | 40000 | 3
2004-02-01 | Design high-fidelity mockups for home and menu screens | UI/UX Designer | 12 | 2500 | 30000 | 4
2005-02-01 | Design shopping cart and checkout flow | UI/UX Designer | 10 | 2500 | 25000 | 4
2006-02-01 | Design order tracking interface with map | UI/UX Designer | 10 | 2500 | 25000 | 4
2007-02-01 | Design profile and order history screens | UI/UX Designer | 8 | 2500 | 20000 | 4
2008-02-01 | Conduct usability testing with target users | UI/UX Designer | 8 | 2500 | 20000 | 5
2001-02-02 | Create rider personas and journey maps | UI/UX Designer | 6 | 2500 | 15000 | 5
2002-02-02 | Design rider dashboard and order assignment interface | UI/UX Designer | 10 | 2500 | 25000 | 5
2003-02-02 | Design navigation and routing screens | UI/UX Designer | 8 | 2500 | 20000 | 5
2004-02-02 | Design delivery confirmation flow | UI/UX Designer | 6 | 2500 | 15000 | 5
2005-02-02 | Design earnings and performance dashboard | UI/UX Designer | 8 | 2500 | 20000 | 5
2006-02-02 | Validate designs with delivery riders | UI/UX Designer | 4 | 2500 | 10000 | 6
2001-02-03 | Design restaurant dashboard and order queue | UI/UX Designer | 10 | 2500 | 25000 | 6
2002-02-03 | Design kitchen display system (KDS) interface | UI/UX Designer | 10 | 2500 | 25000 | 6
2003-02-03 | Design menu and inventory management screens | UI/UX Designer | 8 | 2500 | 20000 | 6
2004-02-03 | Design sales reporting interface | UI/UX Designer | 8 | 2500 | 20000 | 6
2005-02-03 | Validate designs with restaurant staff | UI/UX Designer | 4 | 2500 | 10000 | 6
2006-02-03 | Create design system and component library | UI/UX Designer | 12 | 2500 | 30000 | 6
2001-02-04 | Design admin dashboard with key metrics | UI/UX Designer | 10 | 2500 | 25000 | 6
2002-02-04 | Design analytics and reporting interfaces | UI/UX Designer | 10 | 2500 | 25000 | 6
2003-02-04 | Design user and system management screens | UI/UX Designer | 8 | 2500 | 20000 | 6
2004-02-04 | Design promotional campaign management interface | UI/UX Designer | 8 | 2500 | 20000 | 6
2001-02-05 | Create entity-relationship diagram (ERD) | Database Administrator | 12 | 3500 | 42000 | 5
2002-02-05 | Design user, authentication, and profile tables | Database Administrator | 8 | 3500 | 28000 | 5
2003-02-05 | Design menu, category, and item tables | Database Administrator | 6 | 3500 | 21000 | 5
2004-02-05 | Design order and order items tables | Database Administrator | 8 | 3500 | 28000 | 5
2005-02-05 | Design payment and transaction tables | Database Administrator | 6 | 3500 | 21000 | 5
2006-02-05 | Design delivery, rider, and tracking tables | Database Administrator | 8 | 3500 | 28000 | 6
2007-02-05 | Design loyalty program and promotional tables | Database Administrator | 6 | 3500 | 21000 | 6
2008-02-05 | Normalize schema and create indexing strategy | Database Administrator | 10 | 3500 | 35000 | 6
2001-03-01 | Set up Node.js backend framework and structure | Backend Developer | 8 | 3000 | 24000 | 7
2002-03-01 | Configure PostgreSQL database with migrations | Database Administrator | 8 | 3500 | 28000 | 7
2003-03-01 | Set up Redis caching layer | Backend Developer | 6 | 3000 | 18000 | 7
2004-03-01 | Implement JWT authentication and authorization | Backend Developer | 12 | 3000 | 36000 | 7
2005-03-01 | Implement user registration and OTP verification | Backend Developer | 10 | 3000 | 30000 | 8
2006-03-01 | Implement password reset functionality | Backend Developer | 6 | 3000 | 18000 | 8
2007-03-01 | Implement role-based access control (RBAC) | Backend Developer | 10 | 3000 | 30000 | 8
2008-03-01 | Set up API rate limiting and error handling | Backend Developer | 8 | 3000 | 24000 | 8
2009-03-01 | Implement logging and monitoring services | Backend Developer | 8 | 3000 | 24000 | 8
2010-03-01 | Set up API documentation (Swagger/OpenAPI) | Backend Developer | 6 | 3000 | 18000 | 8
2011-03-01 | Create automated database backup system | Database Administrator | 6 | 3500 | 21000 | 8
2012-03-01 | Implement security middleware and validation | Backend Developer | 8 | 3000 | 24000 | 8
2013-03-01 | Set up testing framework and initial tests | Backend Developer | 8 | 3000 | 24000 | 8
2001-03-02 | Implement menu management APIs (CRUD) | Backend Developer | 10 | 3000 | 30000 | 9
2002-03-02 | Implement shopping cart APIs | Backend Developer | 8 | 3000 | 24000 | 9
2003-03-02 | Implement order placement and management APIs | Backend Developer | 12 | 3000 | 36000 | 9
2004-03-02 | Implement order status update workflow | Backend Developer | 8 | 3000 | 24000 | 9
2005-03-02 | Implement real-time tracking with WebSocket | Backend Developer | 12 | 3000 | 36000 | 10
2006-03-02 | Integrate Stripe payment gateway | Backend Developer | 12 | 3000 | 36000 | 10
2007-03-02 | Integrate JazzCash payment API | Backend Developer | 10 | 3000 | 30000 | 10
2008-03-02 | Integrate EasyPaisa payment API | Backend Developer | 10 | 3000 | 30000 | 10
2009-03-02 | Implement payment webhook handlers | Backend Developer | 8 | 3000 | 24000 | 10
2010-03-02 | Integrate Google Maps API (geocoding, routing) | Backend Developer | 10 | 3000 | 30000 | 11
2011-03-02 | Implement rider assignment algorithm | Backend Developer | 12 | 3000 | 36000 | 11
2012-03-02 | Implement rider location tracking API | Backend Developer | 10 | 3000 | 30000 | 11
2013-03-02 | Integrate Firebase Cloud Messaging (FCM) | Backend Developer | 8 | 3000 | 24000 | 11
2014-03-02 | Integrate Twilio SMS service | Backend Developer | 6 | 3000 | 18000 | 11
2015-03-02 | Implement notification scheduling service | Backend Developer | 8 | 3000 | 24000 | 11
2016-03-02 | Implement loyalty points calculation engine | Backend Developer | 8 | 3000 | 24000 | 12
2017-03-02 | Implement promotional code validation API | Backend Developer | 6 | 3000 | 18000 | 12
2001-03-03 | Set up React Native project structure | Frontend Developer | 6 | 3000 | 18000 | 9
2002-03-03 | Implement splash screen and onboarding | Frontend Developer | 6 | 3000 | 18000 | 9
2003-03-03 | Implement user registration and login flow | Frontend Developer | 10 | 3000 | 30000 | 9
2004-03-03 | Implement home screen with promotions | Frontend Developer | 8 | 3000 | 24000 | 9
2005-03-03 | Implement menu browsing with categories | Frontend Developer | 10 | 3000 | 30000 | 10
2006-03-03 | Implement search and filtering functionality | Frontend Developer | 8 | 3000 | 24000 | 10
2007-03-03 | Implement product detail and customization | Frontend Developer | 8 | 3000 | 24000 | 10
2008-03-03 | Implement shopping cart management | Frontend Developer | 10 | 3000 | 30000 | 10
2009-03-03 | Implement checkout and payment integration | Frontend Developer | 12 | 3000 | 36000 | 11
2010-03-03 | Implement order tracking with live map | Frontend Developer | 12 | 3000 | 36000 | 11
2011-03-03 | Implement push notification handling | Frontend Developer | 6 | 3000 | 18000 | 11
2012-03-03 | Implement order history and reordering | Frontend Developer | 8 | 3000 | 24000 | 11
2013-03-03 | Implement user profile management | Frontend Developer | 8 | 3000 | 24000 | 12
2014-03-03 | Implement ratings and review system | Frontend Developer | 8 | 3000 | 24000 | 12
2015-03-03 | Optimize performance and test on devices | Frontend Developer | 12 | 3000 | 36000 | 12
2001-03-04 | Set up Android project for rider app | Frontend Developer | 6 | 3000 | 18000 | 12
2002-03-04 | Implement rider authentication and profile | Frontend Developer | 8 | 3000 | 24000 | 12
2003-03-04 | Implement order list and assignment screen | Frontend Developer | 10 | 3000 | 30000 | 13
2004-03-04 | Implement order acceptance/rejection flow | Frontend Developer | 6 | 3000 | 18000 | 13
2005-03-04 | Implement Google Maps navigation integration | Frontend Developer | 10 | 3000 | 30000 | 13
2006-03-04 | Implement background GPS tracking service | Frontend Developer | 12 | 3000 | 36000 | 13
2007-03-04 | Implement customer communication (call/message) | Frontend Developer | 6 | 3000 | 18000 | 13
2008-03-04 | Implement delivery confirmation with PIN | Frontend Developer | 8 | 3000 | 24000 | 14
2009-03-04 | Implement earnings and performance dashboard | Frontend Developer | 10 | 3000 | 30000 | 14
2010-03-04 | Implement availability toggle and optimize battery | Frontend Developer | 8 | 3000 | 24000 | 14
2001-03-05 | Set up React.js project for restaurant portal | Frontend Developer | 6 | 3000 | 18000 | 14
2002-03-05 | Implement staff authentication system | Frontend Developer | 6 | 3000 | 18000 | 14
2003-03-05 | Implement real-time order queue with alerts | Frontend Developer | 12 | 3000 | 36000 | 14
2004-03-05 | Implement order details and status updates | Frontend Developer | 8 | 3000 | 24000 | 15
2005-03-05 | Implement menu management interface | Frontend Developer | 10 | 3000 | 30000 | 15
2006-03-05 | Implement inventory management | Frontend Developer | 8 | 3000 | 24000 | 15
2007-03-05 | Implement sales reports and analytics | Frontend Developer | 10 | 3000 | 30000 | 15
2001-03-06 | Set up admin dashboard project structure | Frontend Developer | 6 | 3000 | 18000 | 15
2002-03-06 | Implement admin authentication and authorization | Frontend Developer | 6 | 3000 | 18000 | 15
2003-03-06 | Implement operational dashboard with real-time metrics | Frontend Developer | 12 | 3000 | 36000 | 16
2004-03-06 | Implement analytics and reporting visualizations | Frontend Developer | 12 | 3000 | 36000 | 16
2005-03-06 | Implement user management (customers, riders, staff) | Frontend Developer | 10 | 3000 | 30000 | 16
2006-03-06 | Implement promotional campaign and system configuration | Frontend Developer | 10 | 3000 | 30000 | 16
2001-04-01 | Create comprehensive test plan and strategy | QA Tester | 10 | 2500 | 25000 | 17
2002-04-01 | Define test scenarios and create test cases | QA Tester | 16 | 2500 | 40000 | 17
2003-04-01 | Set up test environment and prepare test data | QA Tester | 8 | 2500 | 20000 | 17
2001-04-02 | Execute customer app functional tests | QA Tester | 16 | 2500 | 40000 | 18
2002-04-02 | Execute rider app functional tests | QA Tester | 12 | 2500 | 30000 | 18
2003-04-02 | Execute restaurant portal functional tests | QA Tester | 12 | 2500 | 30000 | 18
2004-04-02 | Execute admin dashboard functional tests | QA Tester | 12 | 2500 | 30000 | 18
2005-04-02 | Test payment gateway integrations end-to-end | QA Tester | 10 | 2500 | 25000 | 19
2006-04-02 | Test notification services (SMS and push) | QA Tester | 6 | 2500 | 15000 | 19
2007-04-02 | Test complete order workflow from placement to delivery | QA Tester | 12 | 2500 | 30000 | 19
2008-04-02 | Document defects and execute regression testing | QA Tester | 12 | 2500 | 30000 | 19
2001-04-03 | Conduct load testing (200 concurrent users) | QA Tester | 8 | 2500 | 20000 | 19
2002-04-03 | Conduct stress testing (500+ concurrent users) | QA Tester | 8 | 2500 | 20000 | 19
2003-04-03 | Optimize API response times and database queries | Database Administrator | 12 | 3500 | 42000 | 20
2004-04-03 | Conduct security vulnerability scanning | External Auditor | 8 | 8000 | 64000 | 20
2005-04-03 | Perform penetration testing on all systems | External Auditor | 12 | 8000 | 96000 | 20
2006-04-03 | Address all critical security vulnerabilities | Backend Developer | 16 | 3000 | 48000 | 20
2001-04-04 | Test customer app on 10+ device models | QA Tester | 12 | 2500 | 30000 | 20
2002-04-04 | Test rider app on 5+ Android devices | QA Tester | 8 | 2500 | 20000 | 20
2003-04-04 | Test web portals across multiple browsers | QA Tester | 8 | 2500 | 20000 | 20
2004-04-04 | Conduct user acceptance testing (UAT) with stakeholders | Business Analyst | 12 | 3500 | 42000 | 20
2005-04-04 | Obtain UAT sign-off and approval | Project Manager | 4 | 5000 | 20000 | 20
2001-05-01 | Provision production cloud servers (AWS/GCP) | Technical Lead | 8 | 4500 | 36000 | 21
2002-05-01 | Configure load balancer and auto-scaling | Backend Developer | 8 | 3000 | 24000 | 21
2003-05-01 | Set up production database with replication | Database Administrator | 10 | 3500 | 35000 | 21
2004-05-01 | Configure Redis cache cluster | Backend Developer | 6 | 3000 | 18000 | 21
2005-05-01 | Set up CDN for static assets | Backend Developer | 4 | 3000 | 12000 | 21
2006-05-01 | Install SSL certificates and configure HTTPS | Backend Developer | 4 | 3000 | 12000 | 21
2007-05-01 | Set up monitoring, alerting, and logging systems | Backend Developer | 8 | 3000 | 24000 | 21
2008-05-01 | Configure automated backup and disaster recovery | Database Administrator | 8 | 3500 | 28000 | 21
2001-05-02 | Deploy backend APIs to production | Backend Developer | 6 | 3000 | 18000 | 22
2002-05-02 | Deploy admin dashboard to production | Frontend Developer | 4 | 3000 | 12000 | 22
2003-05-02 | Deploy restaurant portal to production | Frontend Developer | 4 | 3000 | 12000 | 22
2004-05-02 | Submit and publish customer app to App Store | Frontend Developer | 6 | 3000 | 18000 | 22
2005-05-02 | Submit and publish customer app to Google Play | Frontend Developer | 6 | 3000 | 18000 | 22
2006-05-02 | Submit and publish rider app to Google Play | Frontend Developer | 6 | 3000 | 18000 | 22
2007-05-02 | Conduct production smoke testing and validation | QA Tester | 8 | 2500 | 20000 | 22
2001-06-01 | Define delivery zones and configure pricing | Delivery Operations Manager | 8 | 3000 | 24000 | 21
2002-06-01 | Procure delivery bags, uniforms, and equipment | Rider Coordinator | 12 | 2500 | 30000 | 21
2003-06-01 | Recruit and interview 20 delivery riders | Rider Coordinator | 40 | 2500 | 100000 | 21
2004-06-01 | Complete rider onboarding and documentation | Rider Coordinator | 16 | 2500 | 40000 | 22
2005-06-01 | Distribute equipment and uniforms to riders | Rider Coordinator | 8 | 2500 | 20000 | 22
2006-06-01 | Set up rider scheduling and zone assignments | Delivery Operations Manager | 8 | 3000 | 24000 | 22
2001-06-02 | Develop training materials for all user types | Business Analyst | 16 | 3500 | 56000 | 21
2002-06-02 | Create video tutorials and documentation | Business Analyst | 12 | 3500 | 42000 | 21
2003-06-02 | Conduct 2-day restaurant staff training workshop | Business Analyst | 16 | 3500 | 56000 | 22
2004-06-02 | Conduct 3-day delivery rider training program | Delivery Operations Manager | 24 | 3000 | 72000 | 22
2005-06-02 | Conduct admin dashboard training for management | Project Manager | 4 | 5000 | 20000 | 22
2006-06-02 | Evaluate training effectiveness with assessments | Business Analyst | 6 | 3500 | 21000 | 22
2001-06-03 | Develop brand identity and marketing guidelines | Marketing Manager | 12 | 3000 | 36000 | 21
2002-06-03 | Create social media content and campaigns | Marketing Manager | 16 | 3000 | 48000 | 21
2003-06-03 | Design in-store promotional materials | UI/UX Designer | 10 | 2500 | 25000 | 22
2004-06-03 | Set up launch promotions (25% off, referral program) | Marketing Manager | 6 | 3000 | 18000 | 22
2005-06-03 | Configure loyalty program in system | Backend Developer | 6 | 3000 | 18000 | 22
2001-07-01 | Launch with limited delivery zone (Week 23) | Project Manager | 8 | 5000 | 40000 | 23
2002-07-01 | Monitor system performance 24/7 | Technical Lead | 40 | 4500 | 180000 | 23
2003-07-01 | Collect user feedback and address issues | Business Analyst | 20 | 3500 | 70000 | 23
2004-07-01 | Optimize workflows based on real operations | Delivery Operations Manager | 16 | 3000 | 48000 | 23
2001-07-02 | Execute full marketing campaign | Marketing Manager | 12 | 3000 | 36000 | 24
2002-07-02 | Expand delivery zones progressively | Delivery Operations Manager | 12 | 3000 | 36000 | 24
2003-07-02 | Scale rider fleet based on demand | Rider Coordinator | 16 | 2500 | 40000 | 25
2004-07-02 | Monitor KPIs and customer acquisition | Project Manager | 12 | 5000 | 60000 | 25
2001-07-03 | Conduct post-launch performance review | Project Manager | 8 | 5000 | 40000 | 26
2002-07-03 | Document lessons learned | Project Manager | 8 | 5000 | 40000 | 26
2003-07-03 | Create project closure report | Project Manager | 12 | 5000 | 60000 | 26
2004-07-03 | Handover to operations team with final presentation | Project Manager | 6 | 5000 | 30000 | 26

## resource_sheet
Column1 | Column2 | Column3 | Column4 | Column5
Resource Name | Type | Hourly Rate (PKR) | Total Hours | Total Cost (PKR)
Backend Developer | Labor | 3000 | 318.0 | 954000.00
Branch Manager | Labor | 3500 | 0.0 | 0.00
Business Analyst | Labor | 3500 | 148.0 | 518000.00
Database Administrator | Labor | 3500 | 108.0 | 378000.00
Delivery Operations Manager | Labor | 3000 | 68.0 | 204000.00
External Auditor | Labor | 8000 | 20.0 | 160000.00
Frontend Developer | Labor | 3000 | 358.0 | 1074000.00
Legal Consultant | Labor | 5000 | 0.0 | 0.00
Marketing Manager | Labor | 3000 | 46.0 | 138000.00
Project Manager | Labor | 5000 | 98.0 | 490000.00
QA Tester | Labor | 2500 | 178.0 | 445000.00
Rider Coordinator | Labor | 2500 | 92.0 | 230000.00
Technical Lead | Labor | 4500 | 94.0 | 423000.00
UI/UX Designer | Labor | 2500 | 226.0 | 565000.00
Fixed Cost Items | Type | Unit Cost | Quantity | Total Cost (PKR)
Background Checks (20 riders) | Fixed | 20000 | 1 | 20000
Cloud Setup Fees | Fixed | 30000 | 1 | 30000
Delivery Bags (30 units) | Fixed | 150000 | 1 | 150000
Development Licenses | Fixed | 50000 | 1 | 50000
Google Maps API Credits | Fixed | 25000 | 1 | 25000
Job Advertisement Postings | Fixed | 10000 | 1 | 10000
Legal Consultation | Fixed | 50000 | 1 | 50000
Marketing Materials Printing | Fixed | 50000 | 1 | 50000
Professional Photography | Fixed | 30000 | 1 | 30000
Rider Uniforms (20 sets) | Fixed | 60000 | 1 | 60000
SMS Gateway Credits | Fixed | 15000 | 1 | 15000
SSL Certificates | Fixed | 15000 | 1 | 15000
Security Audit | Fixed | 100000 | 1 | 100000
Smartphone Accessories | Fixed | 50000 | 1 | 50000
Vehicle Branding | Fixed | 40000 | 1 | 40000
Video Production | Fixed | 80000 | 1 | 80000